# CHA Employee Portal — Phase 2 Project Plan

Goal: Load real CHA employee data into the portal and run it in parallel with CHA's existing system for ~30 days, so staff and leadership can validate it before cutting over to production as the system of record.

Status as of 2026-08-14: CHA has confirmed they're ready to move forward. Supabase project (hplqasxmldqlupbmrpko) confirmed healthy and reachable; schema is applied but empty. See LEVEL_OF_EFFORT.md Phase 2 for hour estimates behind each milestone below.

## Milestone 1 — Wire remaining pages to real data

Replace src/lib/mock-data.ts usage with real Supabase queries, following the pattern already established for Admin Users (src/app/actions/employees.ts + AdminUsersClient.tsx).

☐ Dashboard — leave balance cards, recent requests, timesheet alert

☐ Request — leave request form writes to leave_requests

☐ History — reads real leave_requests for the logged-in employee

☐ Approvals — CEO queue reads/writes real leave_requests status

☐ Calendar — team leave calendar reads real approved requests

☐ Reports — bi-weekly export view; add a Timesheets tab with a manager-rollup query (per existing instruction, stays inside Reports rather than a separate page)

☐ Timesheet — bi-weekly editable grid reads/writes timesheets + timesheet_rows

## Milestone 2 — Accrual engine

☐ Build a function that calculates PTO/sick accrual per pay period by tenure tier and writes accrual_log rows

☐ Apply the 400-hr PTO carryover cap and the uncapped sick policy

☐ Update leave_balances from the accrual log rather than hand-editing balances

## Milestone 3 — Real data load

☐ Apply supabase-migration-002-employee-address.sql (adds address_line1/2, city, state, postal_code to employees) — not yet applied to the live project; needs the CLI relinked to CHA's Supabase account, or run manually via psql/supabase db push

☐ Send CHA onboarding/Employee_Information_Intake.xlsx — roster, contact info, address, hire date, dept/title

☐ Send CHA onboarding/Leave_Balance_Validation.xlsx — per-employee hire date + CHA's own current PTO/sick/personal balances and rates; sheet auto-calculates the portal's expected tier/accrual rate from hire date and flags any mismatch or 400-hr cap violation before data goes live

☐ Resolve any flagged discrepancies with CHA (rate mismatch, over-cap balance) before seeding

☐ Seed employees + leave_balances from the validated data

☐ Confirm Nico Sanders (CEO/approver) and each manager are correctly represented with the right role

## Milestone 4 — Auth & access

☐ Create a real Supabase Auth user per employee (not the cha-demo mock-mode cookie bypass)

☐ Map each Auth user to their employees row

☐ Verify role-based access: employee / manager / admin views resolve correctly for real logins

## Milestone 5 — QA / UAT

☐ Walk every page end-to-end as an employee, a manager, and the admin/CEO role

☐ Confirm exports (CSV/PDF for timesheets and leave reports) match expected real data

☐ Fix anything broken before the pilot starts — don't start the parallel run on a known-broken flow

## Milestone 6 — Parallel run (≈30 days)

☐ CHA staff use both the portal and their existing system side by side

☐ Weekly check-in: compare portal balances/timesheets against the existing system's records, log discrepancies

☐ Track a running list of bugs/gaps found during real use; patch as they surface

☐ End-of-pilot review with CHA leadership: go/no-go decision on cutover

## Milestone 7 — Production cutover (post-pilot, pending go decision)

☐ Point portal.communityhousingassociates.org CNAME at Vercel (Vercel side is already configured — DNS-only step)

☐ Retire/replace the existing system per CHA's own timeline

☐ Remove any remaining demo/mock artifacts (cha-demo cookie bypass, /scope walkthrough page) if CHA wants a clean production instance

## Open questions for CHA

Format/source of the current employee roster and balance data (spreadsheet? existing HR system export?)

Exact go-live date to anchor the "current balance as of X" data pull

Who owns weekly discrepancy triage during the parallel run — CHA staff, or flagged back here?